## WBS
Work Breakdown Structure | [7 empty] | Library Management
| Project Start | 2023-11-25
Level | WBS | Task Description | Predecessor | Assigned To | Start | End | Duration | Notes
1 | 1 | Phase 1: Initiate project |  |  |  |  | 7
2 | 1.1 | Creat project charter |  | Hoaibm | 2023-11-25 | 2023-11-28 | 4
2 | 1.2 | Creat project plan | 1.1 | Hoaibm | 2023-11-29 | 2023-12-01 | 3
1 | 2 | Phase 2: Analyse requirement |  |  |  |  | 11.5
2 | 2.1 | Elicitation | 1.1 | NgaTT | 2023-12-04 | 2023-12-08 | 5
3 | 2.1.1 | Libararian survey | 1.1 | NgaTT | 2023-12-04 | 2023-12-06
3 | 2.1.2 | Student survey | 1.1 | NgaTT | 2023-12-07 | 2023-12-08
2 | 2.2 | Document |  | NgaTT | 2023-12-11 | 2023-12-15 | 5
3 | 2.2.1 | Draw wireframe | 2.1 | NgaTT | 2023-12-11 | 2023-12-12
3 | 2.2.2 | Write SRS | 2.1 | NgaTT | 2023-12-13 | 2023-12-15
2 | 2.3 | Review + update SRS | 2.2.1, 2.2.2 | NgaTT, HoaiBM, Duy OT | 2023-12-18 | 2023-12-18 | 1.5
1 | 3 | Phase 3: Design |  |  |  |  | 5.5
2 | 3.1 | Design UI | 2.2.1 | AnhND | 2023-12-13 | 2023-12-14 | 2
2 | 3.2 | Design DB | 2.2.2 | DuyOT | 2023-12-19 | 2023-12-19 | 1
| 3.3 | Design architecture system | 2.2.2 | DuyOT | 2023-12-20 | 2023-12-20 | 1
2 | 3.4 | Review DB, Architecture system | 3.2, 3.3 | DuyOT, HoaiBM, NgaTT | 2023-12-21 | 2023-12-21 | 1.5
1 | 4 | Phase 4: Implementation |  |  |  |  | 26.5
2 | 4.1 | Inter 1 |  |  |  |  | 12
3 | 4.1.1 | Account Management | 3.1, 3.2, 3.3 | AnhH | 2023-12-21 | 2023-12-26
4 | 4.1.1.1 | Login |  | AnhH | 2023-12-21 | 2023-12-21 | 0.5
4 | 4.1.1.2 | Logout |  | AnhH | 2023-12-21 | 2023-12-21 | 0.5
4 | 4.1.1.3 | Register account |  | AnhH | 2023-12-22 | 2023-12-22 | 1
4 | 4.1.1.4 | View profile |  | AnhH | 2023-12-25 | 2023-12-25 | 0.5
4 | 4.1.1.5 | Update profile |  | AnhH | 2023-12-25 | 2023-12-25 | 0.5
4 | 4.1.1.6 | View account list |  | AnhH | 2023-12-26 | 2023-12-26 | 0.5
4 | 4.1.1.7 | View accout detail |  | AnhH | 2023-12-26 | 2023-12-26 | 0.5
3 | 4.1.2 | Book Management | 3.1, 3.2, 3.3 | TuanH
4 | 4.1.2.1 | View book list |  | TuanH | 2023-12-21 | 2023-12-21 | 0.5
4 | 4.1.2.2 | View book detail |  | TuanH | 2023-12-21 | 2023-12-21 | 0.5
4 | 4.1.2.3 | Search book |  | TuanH | 2023-12-22 | 2023-12-22 | 0.5
4 | 4.1.1.4 | Add book |  | TuanH | 2023-12-22 | 2023-12-25 | 1.5
4 | 4.1.1.5 | Update book |  | TuanH | 2023-12-26 | 2023-12-26 | 0.5
4 | 4.1.1.6 | Delete book |  | TuanH | 2023-12-26 | 2023-12-26 | 0.5
| 4.1.3 | Fix bug release 1 |  | AnhH, TuanH | 2023-12-27 | 2023-12-28 | 4
2 | 4.2 | Inter 2 |  |  |  |  | 14.5
3 | 4.2.1 | Borrow book | 3.1, 3.2, 3.3 | AnhH
4 | 4.2.1.1 | Add book to cart |  | AnhH | 2023-12-29 | 2023-12-29 | 0.5
4 | 4.2.1.2 | View cart |  | AnhH | 2023-12-29 | 2023-12-29 | 0.5
4 | 4.2.1.3 | Creat ticket borrow book |  | AnhH | 2024-01-02 | 2024-01-02 | 1
4 | 4.2.1.4 | Approve borrow book |  | AnhH | 2024-01-03 | 2024-01-03 | 0.5
4 | 4.2.1.5 | View borrowed book list |  | AnhH | 2024-01-03 | 2024-01-03 | 0.5
4 | 4.2.1.6 | Update ticket borrow book |  | AnhH | 2024-01-04 | 2024-01-04 | 1
4 | 4.2.1.7 | Delete ticket borrow book |  | AnhH | 2024-01-05 | 2024-01-05 | 0.5
3 | 4.2.2 | Return book | 3.1, 3.2, 3.3 | TuanH
4 | 4.2.2.1 | Confirm return book |  | TuanH | 2023-12-29 | 2023-12-29 | 0.5
4 | 4.2.2.2 | View returned book list |  | TuanH | 2024-01-02 | 2024-01-02 | 1
3 | 4.2.3 | Rate and comment | 3.1, 3.2, 3.3 | TuanH
4 | 4.2.3.1 | Creat rate |  | TuanH | 2024-01-03 | 2024-01-03 | 1
4 | 4.2.3.2 | Creat comment |  | TuanH | 2024-01-04 | 2024-01-04 | 1
4 | 4.2.3.3 | View comment |  | TuanH | 2024-01-05 | 2024-01-05 | 0.5
3 | 4.2.3 | Fix bug release 2 |  | AnhH, TuanH | 2024-01-08 | 2023-01-10 | 6
1 | 5 | Phase 5: Testing |  |  |  |  | 13
2 | 5.1 | Creat Test plan | 1.1, 1.2 | DuyOT | 2023-12-04 | 2023-12-04 | 1
2 | 5.2 | Write testcase | 2.3 | DuyOT | 2023-12-19 | 2023-12-21 | 3
2 | 5.3 | Implement test release 1 | 4.1 | DuyOT | 2023-12-27 | 2023-12-29 | 3
| 5.4 | Implement test release 2 | 4.2 | DuyOT | 2024-01-08 | 2024-01-10 | 3
2 | 5.5 | Implement testing in all function | 4.1.3, 4.2.3 | DuyOT | 2024-01-11 | 2024-01-12 | 2
2 | 5.6 | UAT | 5.5 | DuyOT | 2024-01-15 | 2024-01-15 | 1
1 | 6 | Phase 6: Deployment |  |  |  |  | 5.4
2 | 6.1 | Buy server, test device | 1.1 | MinhTT |  | 2023-12-21 | 1
2 | 6.2 | Setting server | 6.1 | HaiDT | 2023-12-22 | 2023-12-22 | 1
2 | 6.3 | Deploy code release 1 in staging enviroment | 6.2, 4.1 | HaiDT | 2023-12-26 | 2023-12-26 | 0.2
Testing in staging enviroment
2 | 6.4 | Deploy code release 2 in staging enviroment | 6.2, 4.2 | HaiDT | 2023-01-05 | 2023-01-05 | 0.2
2 | 6.5 | Deploy code in product enviroment | 5.5 | HaiDT | 2024-01-16 | 2024-01-16 | 1
2 | 6.6 | Testing in product enviroment | 6.4 | DuyOT | 2024-01-17 | 2023-01-18 | 2
2
77.9