## Sheet1
Risk Management Plan
ID | Risk | Mitigation (biện pháp giảm thiểu) | contingency (dự phòng) | impact | possibility of occurring | priority
1 | If the testing equipment is not delivered three days later than requested, it may result in a delay in the testing schedule and the quality of the delivered product could be compromised | Prioritize test cases; in case of insufficient testing time, prioritize high-priority test cases | Set a deadline for purchasing testing equipment seven days prior to the actual testing start date | High | Low | Medium
2 | If the librarian is unavailable for survey participation, the elicitation process will be delayed, impacting the progress of requirements analysis and SRS documentation | Utilize alternative elicitation methods aligned with the librarian's schedule. In the absence of their availability, a combination of observational techniques and survey responses can be employed. | Provide an additional plan for elicitation using risk-mitigating methods. | Medium | Medium | Medium
3 | If project members take holiday leaves and request additional days off, it will impact the project timeline. If each developer takes an additional 2-day leave, the code delivery timeline will be delayed by an additional 2 days | Clarify the project situation to the project team members, requesting them to minimize leave during holidays. Leaves can be taken after the project concludes | Project plan need buffer 2 days | High | Low | Medium
4 | If the developer team lacks experience, there might be more bugs in the code than anticipated, requiring additional time for testing and bug fixing. This might jeopardize the project timeline | Training for the developer team before development begins, code review prior to deployment. In the BD phase, create the convention ( coding convention, naming convention, coding structure ) | Increase the bug-fixing time by one day. | High | Low | Medium
5 | If the requirements diverge from the actual customer expectations and the acceptance criteria are not met during testing, the project may require redevelopment | Select an experienced Business Analyst to facilitate document reviews with stakeholder participation during scheduled sessions | Calculating additional costs and time if there's a need for reworking the requirements. | High | Low | High
Extreme